## Sheet
Project Name: |  | Date: |  | Report Number: |  | Weather/Temp:
Time / Shift | Work Area / Phase | Trade / Contractor | Number of Workers | Equipment Used | Hours Worked | Activity Description / Progress | Issues / Delays / Safety
07:00 AM | Foundation | ABC Concrete | 5 | Cement Mixer, Pump | 8 | Pouring footings for Sector A | None
08:30 AM | Site-wide | XYZ Electric | 3 | Scissor Lift | 6 | Rough-in wiring for exterior lighting | Material delivery delayed 1 hour
Total Daily Man-Hours: |  |  |  | Site Supervisor Signature: