## Sheet
Task ID | Category | Task Description | Assigned To | Due Date | Status | Completion Date | Notes
EP-001 | Venue | Confirm site booking and deposit | Jane Doe | 2023-10-01 | Completed | 2023-09-28 | Deposit paid via wire transfer
EP-002 | Catering | Finalize menu selection | John Smith | 2023-10-05 | In Progress |  | Awaiting vegan options list
EP-003 | Marketing | Send out digital invitations | Alice Wong | 2023-10-10 | Completed | 2023-10-09 | Sent to all 500 subscribers
EP-004 | Audio/Visual | Hire equipment rental service | Bob Miller | 2023-10-15 | Not Started |  | Comparing quotes from 3 vendors
EP-005 | Budget | Final budget reconciliation | Jane Doe | 2023-11-01 | Not Started |  | Post-event task