## Sheet
Project / Task Description | Room/Area | Priority | Status | Estimated Cost | Actual Cost | Variance
New Hardwood Flooring | Living Room | High | In Progress | $3,500.00 | $3,200.00 | $300.00
Recessed Lighting Installation | Kitchen | Medium | Completed | $800.00 | $950.00 | -$150.00
Interior Wall Painting | Master Bedroom | Low | Not Started | $450.00 | $0.00 | $450.00
Cabinet Hardware Upgrade | Bathroom | Medium | Completed | $150.00 | $140.00 | $10.00
Smart Thermostat Installation | Hallway | Medium | Not Started | $250.00 | $0.00 | $250.00
TOTALS |  |  |  | $5,150.00 | $4,290.00 | $860.00