## Sheet
Milestone ID | Task Description | Owner | Start Date | Target Date | Status | % Complete | Notes / Blockers
M1-001 | Project Kick-off & Stakeholder Alignment | Sarah Chen | 2023-11-01 | 2023-11-05 | Completed | 100% | All approvals received.
M1-002 | Requirement Documentation Phase | James Wilson | 2023-11-06 | 2023-11-15 | In Progress | 65% | Awaiting feedback on Section 4.
M1-003 | System Architecture Design | Elena Rodriguez | 2023-11-12 | 2023-11-25 | Not Started | 0% | Pending M1-002 completion.
M1-004 | Security Audit & Compliance Review | David Park | 2023-11-20 | 2023-11-30 | On Hold | 10% | Budget review in progress.
M1-005 | Monthly Progress Report | Sarah Chen | 2023-11-28 | 2023-11-30 | In Progress | 20% | Drafting initial findings.