## Sheet
Task ID | Task Description | Assigned To | Start Date | End Date | Priority | Status | % Complete | Notes
101 | Project Initiation | John Doe | 2023-10-01 | 2023-10-05 | High | Completed | 100% | Project charter signed.
102 | Market Research | Jane Smith | 2023-10-06 | 2023-10-15 | Medium | In Progress | 65% | Competitor analysis ongoing.
103 | UI/UX Design | Alex Rivera | 2023-10-16 | 2023-10-30 | High | Not Started | 0% | Awaiting research data.
104 | Backend Development | Sam Wilson | 2023-11-01 | 2023-12-15 | High | Not Started | 0% | Database schema pending.
105 | Quality Assurance | Emily Chen | 2023-12-16 | 2023-12-24 | Medium | Not Started | 0% | -