## Sheet
Inspection ID | Date | Site Location / Area | Inspector Name | Safety Category | Observation / Hazard Identified | Risk Level (Low/Med/High) | Corrective Action Required | Assigned To | Due Date | Status (Open/Closed) | Date Closed
SI-001 | 2023-10-01 | North Wing - Floor 2 | John Doe | PPE | Worker observed without hard hat in active zone. | Medium | Issue immediate warning and provide spare helmet. | Site Foreman | 2023-10-01 | Closed | 2023-10-01
SI-002 | 2023-10-02 | Excavation Site A | Jane Smith | Fall Protection | Guardrail missing on eastern perimeter. | High | Install temporary barricades and permanent rails. | Safety Officer | 2023-10-03 | Open
SI-003 | 2023-10-02 | Storage Yard | John Doe | Fire Safety | Fire extinguisher inspection tag expired. | Low | Replace or re-certify extinguisher. | Maintenance Team | 2023-10-05 | In Progress
SI-004 | 2023-10-03 | Electrical Room | Robert Brown | Electrical | Exposed wiring near temporary panel. | High | De-energize and secure wiring in junction box. | Chief Electrician | 2023-10-03 | Closed | 2023-10-03
SI-005 | 2023-10-04 | General Site | Jane Smith | Housekeeping | Excess debris blocking emergency exit path. | Medium | Clear path and schedule daily waste removal. | Labor Crew | 2023-10-04 | Open