## Sheet
Subcontractor Name | Trade / Scope | Contact Person | Work Quality (1-5) | Schedule Adherence | Safety Compliance | Communication | Contract Value ($) | % Complete | Project Status
Foundation Specialists Inc. | Concrete & Foundation | John Smith | 5 | On Schedule | Excellent | Good | 150,000 | 100% | Completed
Elite Electrical Services | Electrical / Wiring | Sarah Miller | 4 | 2 Days Late | Satisfactory | Excellent | 85,000 | 65% | Active
Rapid Plumbing Co. | Plumbing & HVAC | Mike Ross | 2 | Significant Delay | Needs Improvement | Poor | 120,000 | 30% | Delayed
Modern Framing Ltd. | Structural Wood Framing | David Chen | 4 | On Schedule | Excellent | Good | 210,000 | 90% | Active
Precision Roofing | Roofing & Waterproofing | Anna White | 5 | Ahead of Schedule | Excellent | Excellent | 95,000 | 0% | Pending Start