## Sheet
ID | Task Description | Owner | Priority | Due Date | Status | Notes/Comments
1 | Define project scope and deliverables | Project Manager | High | 2023-10-27 | In Progress | Awaiting final sign-off from stakeholders.
2 | Internal team kickoff meeting | Team Lead | Medium | 2023-10-28 | Not Started | Scheduled for 10:00 AM.
3 | Review budget allocations | Finance | High | 2023-10-30 | Completed | Budget approved for Q4.
4 | Draft technical requirements document | Lead Developer | Medium | 2023-11-02 | In Progress | Draft 50% complete.
5 | Client feedback session | Account Manager | Low | 2023-11-05 | Not Started | Pending client availability.