## Sheet
Task ID | User Story / Task Description | Assignee | Priority | Status | Story Points | Estimated Hours | Actual Hours | Start Date | Due Date
SPT-001 | User login authentication module | John Doe | High | In Progress | 5 | 10 | 4 | 2023-10-01 | 2023-10-05
SPT-002 | Database schema migration | Jane Smith | Medium | Done | 3 | 6 | 5 | 2023-10-01 | 2023-10-02
SPT-003 | API documentation update | Mike Ross | Low | To Do | 2 | 4 | 0 | 2023-10-06 | 2023-10-07
SPT-004 | Password reset functionality | John Doe | High | To Do | 3 | 8 | 0 | 2023-10-08 | 2023-10-10
SPT-005 | UI responsive design fixes | Sarah Connor | Medium | In Progress | 8 | 16 | 12 | 2023-10-01 | 2023-10-09