## Sheet
Resource ID | Resource Name | Category (Labor/Equip/Material) | Assigned Project | Task Description | Start Date | End Date | Allocation (%) | Unit Cost ($) | Total Cost ($) | Status
R-001 | Excavator 20T | Equipment | Bridge Site A | Foundation Excavation | 2023-11-01 | 2023-11-15 | 100% | 150.00 | 2,250.00 | In Progress
R-002 | John Smith (Lead) | Labor | Bridge Site A | Site Supervision | 2023-11-01 | 2023-12-20 | 50% | 65.00 | 5,200.00 | In Progress
R-003 | Structural Steel | Material | Downtown Plaza | Frame Assembly | 2023-11-10 | 2023-11-12 | 100% | 500.00 | 15,000.00 | Scheduled
R-004 | Cement Mixer | Equipment | West Roadway | Pavement Pouring | 2023-11-05 | 2023-11-07 | 100% | 80.00 | 240.00 | Completed
R-005 | Sarah Miller | Labor | Downtown Plaza | Safety Inspection | 2023-11-12 | 2023-11-12 | 100% | 75.00 | 600.00 | Pending