## Sheet
Goal ID | Task / Objective | Assigned To | Start Date | Target Date | Status | % Complete | Notes
001 | Initial Requirements Gathering | Project Manager | 2023-10-01 | 2023-10-05 | Completed | 100% | All stakeholders interviewed.
002 | System Design & Architecture | Lead Architect | 2023-10-06 | 2023-10-15 | In Progress | 60% | Reviewing database schema.
003 | Frontend Development | UI Team | 2023-10-16 | 2023-11-01 | Not Started | 0% | Pending design approval.
004 | Quality Assurance Testing | QA Lead | 2023-11-02 | 2023-11-10 | Not Started | 0%
005 | Deployment | DevOps | 2023-11-12 | 2023-11-15 | Not Started | 0%