## Sheet
Task Description | Assigned To | Start Date | End Date | Duration (Days) | Status | Notes
Project Kickoff | Project Manager | 2023-10-01 | 2023-10-01 | 1 | Complete | Initial stakeholder meeting
Requirements Gathering | Analyst | 2023-10-02 | 2023-10-08 | 7 | In Progress | Drafting functional specs
System Design | Lead Architect | 2023-10-09 | 2023-10-20 | 12 | Pending | Review with dev team
Development Phase 1 | Engineering Team | 2023-10-21 | 2023-11-15 | 25 | Pending | Focus on backend infrastructure
User Acceptance Testing | QA Team | 2023-11-16 | 2023-11-30 | 15 | Pending | Client sign-off required