## Sheet
Task ID | Maintenance Item | Location / Unit | Priority | Status | Assigned To | Date Reported | Due Date | Date Completed | Estimated Cost | Actual Cost | Notes
M001 | HVAC Filter Replacement | Unit 204 | Medium | Completed | John Smith | 2023-10-01 | 2023-10-05 | 2023-10-04 | $50.00 | $45.00 | Routine quarterly maintenance.
M002 | Leaking Kitchen Faucet | Unit 105 | High | In Progress | Plumbing Pro Co. | 2023-10-10 | 2023-10-11 |  | $150.00 |  | Parts ordered; waiting for arrival.
M003 | Exterior Painting | Main Building - North Wall | Low | Pending | External Contractor | 2023-09-15 | 2023-11-01 |  | $2,500.00 |  | Weather dependent.
M004 | Smoke Detector Testing | All Common Areas | High | Not Started | Building Manager | 2023-10-12 | 2023-10-15 |  | $0.00 |  | Annual safety inspection.
M005 | Broken Window Pane | Unit 302 | High | Completed | Glass Solutions | 2023-10-05 | 2023-10-06 | 2023-10-06 | $300.00 | $315.00 | Emergency repair after storm.