## Sheet
Task ID | Task Name | Assignee | Start Date | End Date | Duration (Days) | Status | Completion (%)
T-001 | Project Initiation | John Doe | 2023-10-01 | 2023-10-05 | 4 | Completed | 100%
T-002 | Market Research | Jane Smith | 2023-10-06 | 2023-10-15 | 9 | In Progress | 65%
T-003 | Data Analysis | Robert Brown | 2023-10-16 | 2023-10-20 | 4 | Not Started | 0%
T-004 | Drafting Report | Emily White | 2023-10-21 | 2023-10-25 | 4 | Not Started | 0%
T-005 | Final Presentation | John Doe | 2023-10-26 | 2023-10-27 | 1 | Not Started | 0%