## Sheet
Work Order # | Job Description | Client Name | Assigned To | Priority | Start Date | Due Date | Status | Estimated Hours | Actual Hours | Total Cost
WO-1001 | Website Redesign | Acme Corp | John Doe | High | 2023-10-01 | 2023-10-15 | In Progress | 40 | 12 | $2,500
WO-1002 | Database Migration | Global Systems | Jane Smith | Medium | 2023-10-05 | 2023-10-20 | Not Started | 20 | 0 | $1,200
WO-1003 | Security Audit | Tech Solutions | Mike Ross | Critical | 2023-10-08 | 2023-10-10 | Completed | 10 | 11 | $800