## Sheet
ID | Deliverable / Action Item | Owner | Priority | Status | Start Date | Due Date | % Complete | Notes
001 | Project Charter Draft | John Doe | High | Completed | 2023-10-01 | 2023-10-05 | 100% | Approved by sponsor.
002 | Market Research Report | Jane Smith | Medium | In Progress | 2023-10-06 | 2023-10-20 | 45% | Waiting on survey results.
003 | Budget Approval | Finance Team | High | Not Started | 2023-10-21 | 2023-10-25 | 0% | Pending Q4 projections.
004 | User Interface Mockups | Design Dept | Low | On Hold | 2023-10-10 | 2023-10-30 | 10% | Scope change pending.