## Sheet
Task ID | Task Description | Assigned To | Start Date | Due Date | Duration (Days) | % Complete | Status | Priority
101 | Project Initiation & Planning | John Smith | 2023-10-01 | 2023-10-05 | 4 | 100% | Completed | High
102 | Requirements Gathering | Sarah Lee | 2023-10-06 | 2023-10-15 | 9 | 65% | In Progress | High
103 | UI/UX Design Mockups | Mike Ross | 2023-10-16 | 2023-10-25 | 10 | 0% | Not Started | Medium
104 | Backend API Development | Anna Chen | 2023-10-20 | 2023-11-10 | 21 | 15% | In Progress | High
105 | Database Schema Design | Anna Chen | 2023-10-10 | 2023-10-15 | 5 | 100% | Completed | Medium
106 | Quality Assurance Testing | David Miller | 2023-11-15 | 2023-11-30 | 15 | 0% | Not Started | Low