## Sheet
ID | Milestone | Action Item | Owner | Priority | Start Date | Due Date | Status | Notes
1 | Project Kickoff | Define project scope and objectives | Jane Doe | High | 2023-10-01 | 2023-10-05 | Completed | Approved by stakeholders.
2 | Phase 1 Design | Create wireframes for user dashboard | John Smith | Medium | 2023-10-06 | 2023-10-15 | In Progress | Waiting for branding guidelines.
3 | Phase 1 Design | Review technical architecture | Alice Wong | High | 2023-10-10 | 2023-10-20 | Not Started | Internal review scheduled.
4 | Infrastructure Setup | Provision cloud server instances | Bob Miller | High | 2023-10-12 | 2023-10-14 | On Hold | Budget approval pending.