## Sheet
Error ID | Date Reported | Project Phase | Error Category | Description of Issue | Impact Level | Priority | Assigned To | Status | Resolution Date | Root Cause Analysis
ERR-001 | 2023-10-01 | Planning | Budget | Initial cost estimation missed software licensing fees. | High | Critical | Jane Doe | Resolved | 2023-10-05 | Lack of checklist for procurement items.
ERR-002 | 2023-10-03 | Execution | Communication | Stakeholder milestone report not sent on schedule. | Medium | High | John Smith | In Progress |  | Automation script failure.
ERR-003 | 2023-10-10 | Design | Scope | Feature creep: User login requirements expanded without approval. | Low | Medium | Alice Wong | Open |  | Vague requirement documentation.