## Sheet
Milestone / Task Name | Assigned Owner | Priority | Start Date | Target Date | Actual End Date | Status | Budget/Cost | Completion %
Project Kickoff | Project Manager | High | 2023-10-01 | 2023-10-02 | 2023-10-02 | Completed | $0.00 | 100%
Requirement Gathering | Business Analyst | High | 2023-10-03 | 2023-10-15 |  | In Progress | $500.00 | 60%
System Design Phase | Lead Architect | Medium | 2023-10-16 | 2023-10-30 |  | Not Started | $1,200.00 | 0%
Frontend Development | UI Team | Medium | 2023-11-01 | 2023-12-15 |  | Not Started | $3,000.00 | 0%
Backend API Integration | Dev Team | High | 2023-11-01 | 2023-12-15 |  | Not Started | $4,500.00 | 0%
User Acceptance Testing (UAT) | QA Team | High | 2023-12-16 | 2023-12-25 |  | Not Started | $1,000.00 | 0%
Final Deployment | DevOps Team | Critical | 2024-01-01 | 2024-01-02 |  | Not Started | $200.00 | 0%