## Sheet
Task ID | Task Description | Assigned To | Priority | Due Date | Status | Completion Date | Notes
101 | Initial Requirements Gathering | Sarah Jenkins | High | 2023-11-01 | Completed | 2023-10-30 | All stakeholders signed off.
102 | Database Schema Design | Mark Chen | High | 2023-11-05 | Completed | 2023-11-04 | Optimized for high-volume queries.
103 | API Endpoint Development | Alex Rivera | Medium | 2023-11-15 | In Progress | - | Authentication module pending.
104 | Front-end UI Mockups | Emily White | Medium | 2023-11-10 | Completed | 2023-11-09 | V2 mockups approved by UX lead.
105 | Unit Testing Integration | Mark Chen | Low | 2023-11-20 | Not Started | - | Waiting for API completion.
106 | User Acceptance Testing (UAT) | Sarah Jenkins | High | 2023-11-25 | Not Started | - | Scheduled for end of month.