## Sheet
Task ID | Task Name | Assigned To | Priority | Status | Start Date | Due Date | % Complete | Notes
001 | Project Kickoff | Project Manager | High | Completed | 2023-10-01 | 2023-10-01 | 100% | Initial meeting successful
002 | Requirements Gathering | Business Analyst | High | In Progress | 2023-10-02 | 2023-10-10 | 60% | Stakeholder interviews ongoing
003 | UI/UX Design | Designer | Medium | Not Started | 2023-10-11 | 2023-10-20 | 0% | Waiting for requirements
004 | Development - Phase 1 | Lead Developer | High | Not Started | 2023-10-21 | 2023-11-15 | 0% | Pending design approval
005 | Quality Assurance | QA Tester | Medium | Not Started | 2023-11-16 | 2023-11-30 | 0%