## Sheet
Task ID | Task Description | Owner | Priority | Status | Start Date | Due Date | % Complete | Notes / Blockers
101 | Project Kickoff Meeting | Sarah Miller | High | Completed | 2023-10-01 | 2023-10-01 | 100% | All stakeholders attended.
102 | Requirements Gathering | John Doe | High | In Progress | 2023-10-02 | 2023-10-15 | 65% | Waiting on feedback from the marketing team.
103 | UI/UX Design Mockups | Emily Chen | Medium | Not Started | 2023-10-16 | 2023-10-30 | 0% | Pending requirement finalization.
104 | Backend API Development | David Ross | High | At Risk | 2023-10-05 | 2023-10-25 | 30% | Resource shortage due to illness.
105 | Weekly Stakeholder Report | Sarah Miller | Low | On Track | 2023-10-01 | Ongoing | - | Sent every Friday at 4:00 PM.