## Sheet
Task ID | Category | Task Description | Assigned To | Due Date | Status | Estimated Cost | Actual Cost | Notes
101 | Venue | Finalize site selection and sign contract | Jane Doe | 2023-10-15 | Completed | $2,500.00 | $2,450.00 | Deposit paid on 10/12
102 | Catering | Menu tasting and selection | John Smith | 2023-11-01 | In Progress | $1,200.00 | $0.00 | Waiting for vegetarian options
103 | Marketing | Send out digital invitations | Alice Wong | 2023-11-05 | Not Started | $150.00 | $0.00 | Email list being cleaned
104 | Logistics | Confirm AV equipment rental | Bob Miller | 2023-11-10 | In Progress | $500.00 | $500.00 | Invoice received
105 | Entertainment | Book keynote speaker | Jane Doe | 2023-10-20 | Completed | $3,000.00 | $3,000.00 | Travel arrangements confirmed