## Sheet
ID | Task Description | Assigned To | Start Date | End Date | Duration (Days) | Priority | Status | % Complete
101 | Project Kick-off Meeting | Sarah Jenkins | 2023-10-01 | 2023-10-01 | 1 | High | Completed | 100%
102 | Requirement Analysis | Michael Chen | 2023-10-02 | 2023-10-08 | 7 | High | Completed | 100%
103 | UI/UX Design Mockups | Emily White | 2023-10-09 | 2023-10-20 | 12 | Medium | In Progress | 65%
104 | Backend API Development | David Miller | 2023-10-15 | 2023-11-05 | 21 | High | In Progress | 30%
105 | Frontend Integration | Emily White | 2023-11-06 | 2023-11-20 | 14 | Medium | Not Started | 0%
106 | Quality Assurance Testing | Jessica Lee | 2023-11-21 | 2023-12-05 | 15 | High | Not Started | 0%
107 | Final Deployment | Sarah Jenkins | 2023-12-10 | 2023-12-12 | 2 | Critical | Not Started | 0%