## Sheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Budget ($) | Progress (%)
101 | Project Kickoff | John Doe | 2023-10-01 | 2023-10-02 | High | Completed | 500 | 100%
102 | Market Research | Jane Smith | 2023-10-03 | 2023-10-15 | Medium | In Progress | 2,000 | 45%
103 | UI/UX Design Phase | Mike Ross | 2023-10-10 | 2023-11-05 | High | Not Started | 5,500 | 0%
104 | Backend Development | Sarah Connor | 2023-11-01 | 2023-12-20 | High | Not Started | 12,000 | 0%
105 | Quality Assurance | David Miller | 2023-12-21 | 2024-01-10 | Low | Not Started | 3,000 | 0%